## Sheet1
WBS Code | Task Description
1 | Just the Job Computer System | Name : Radhika Amar Desai
1.1 | Requirement Gathering & Analysis | Registration Number : 22BCE1114
1.1.1 | Identify Customer Needs
1.1.2 | Analyze Existing Paperwork Processes
1.1.3 | Define System Requirements
1.2 | System Design
1.2.1 | Database Design
1.2.2 | User Interface Design
1.2.3 | System Architecture Design
1.3 | System Development
1.3.1 | Database Development
1.3.2 | User Interface Development
1.3.3 | Backend Development
1.4 | System Testing
1.4.1 | Unit Testing
1.4.2 | Integration Testing
1.4.3 | User Acceptance Testing
1.5 | System Deployment
1.5.1 | System Installation
1.5.2 | Data Migration
1.5.3 | User Training
1.6 | Post-Deployment Support
1.6.1 | System Maintenance
1.6.2 | Customer Support
1.6.3 | Performance Monitoring